## Sheet1
Requirement ID | Detailed Description | Story Points | Priority | Sprint Number | Labels | Assignees
25 | Voice lines | 1 | 4 | 6 | sfx
33 | Implement a live camera feed into the API | 5 | 3 | 6 | software | m-riley04
34 | Object detection through the camera | 8 | 4 | 6 | software | Ryland-Edwards, m-riley04
91 | Network Issues for polypod.net | 2 | 1 | 6 | bug | hrsmith1, rileyAnde
35 | Emotion detection through camera | 8 | 3 | 6 | software
85 | Have live sports score updates for 'followed' games | 2 | 2 | 6 | software | aidenhburke
92 | Fix top touchscreen | 2 | 1 | 6 | hardware | m-riley04
93 | add weather animations | 3 | 2 | 6 | software | Ryland-Edwards
94 | Polish ui style and theme | 3 | 2 | 6 | software | Ryland-Edwards
95 | Robust Set up process | 5 | 2 | 6 | web app | hrsmith1
97 | Speaker Set up | 3 | 2 | 6 | hardware | rileyAnde
98 | Fix Settings Part | 5 | 1 | 6 | hardware | rileyAnde
89 | Website UI updates | 2 | 2 | 5 |  | ColinTreanor
81 | Poll weather API for live weather updates | 1 | 2 | 5 |  | ColinTreanor, aidenhburke
99 | Display interior environmental data on device | 1 | 2 | 6 | software