## Sheet1
Requirement ID | Detailed Description | Story Points | Priority | Sprint Number | Labels
9 | Connect speaker | 1 | 1 | 1 | hardware
20 | Simple login system that is mobile compatable | 5 | 1 | 1 | software, web app
12 | Connect environmental sensor(s) | 3 | 1 | 1 | hardware
11 | Connect camera | 1 | 1 | 1 | hardware
10 | Connect microphone | 1 | 1 | 1 | hardware
3 | Measure hardware dimensions to begin CAD design of the case | 5 | 1 | 1 | 3D design
32 | Create user database | 5 | 1 | 1 | software
36 | Create bottom screen GUI | 8 | 1 | 1
21 | Allow users to select what they're interested in | 8 | 1 | 1 | software, web app
13 | Hardware startup procedure for polypod device | 3 | 2 | 1 | hardware, software
39 | CRUD operations for Users | 3 | 1 | 1
40 | Create polling system to connect to external APIs | 8 | 1 | 1
37 | Initalize NPM workspace and packages | 1 | 1 | 2
4 | Pet-like maintenance system/stats and interactions (happiness/mood, etc.) | 3 | 3 | 2 | software
5 | Modular data source API system (stocks, sports, ...) | 8 | 1 | 2 | software
14 | RGB LED eyes for conveying emotion | 3 | 2 | 2 | hardware, software
19 | Find APIs for basic notification types | 3 | 2 | 2 | project
6 | Connect website to server | 3 | 1 | 3 | software
15 | Polypod reactions to touch/bumps | 1 | 4 | 3 | hardware, software
16 | Reactions to high/low temperatures | 1 | 4 | 3 | hardware, software
17 | Reactions to loud/sudden sounds | 1 | 4 | 3 | hardware, software
18 | A physical switch to softly shutdown device when not in use | 3 | 2 | 3 | hardware
24 | Create page for current statistics/recorded data | 3 | 2 | 3 | software, web app
31 | Create API for hardware to server | 3 | 2 | 3 | hardware, software
22 | Mobile version of the web-app | 3 | 3 | 4 | software, web app
23 | Live camera feed section | 3 | 2 | 4 | software, web app
26 | Set a visual timer/alarm on the device | 3 | 3 | 4 | software
27 | Polypod reactions to web notifications/api polls | 3 | 1 | 4 | software
7 | Web application can communicate with polypod via API | 5 | 2 | 4 | software, web app
33 | Implement a live camera feed into the API | 5 | 3 | 4 | software
28 | Mouth animation for opening to critter scene | 3 | 2 | 5 | artwork
29 | Animation for critter dance | 5 | 2 | 5 | artwork
30 | Implement screensavers | 3 | 2 | 5 | software
35 | Emotion detection through camera | 8 | 3 | 5 | software
8 | Random movement patterns and ability to follow the user | 8 | 5 | 6 | hardware, software
25 | Voice lines | 1 | 4 | 6 | sfx
34 | Object detection through the camera | 8 | 4 | 6 | software