## Initial Requirements Stack
Requirement ID | Detailed Description | Story Points | Priority | Sprint No. | Group | Group Labels
1 | measure hardware dimensions to begin cad design of the case | 1 | 1 |  | Hardware | Hardware
2 | Pet-like maintenance system/stats and interactions (happiness/mood, etc.). Essentially, tamagachi | 3 | 3 |  | Software | Software
3 | Modular data source API system (stocks, sports, ...) for sending different data from server to polypod without re writing | 8 | 1 |  | Software | Hardware/Software
4 | Connect Website to server | 8 | 4 |  | Software | 3D Design
4 | Web application can communicate with polypod via API | 5 | 1 |  | Software | Project
5 | Random movement patterns and ability to follow/track user | 8 | 5 |  | Hardware/Software | Artwork
6 | Tiny speaker for alerts or little scuttling sounds | 3 | 2 |  | Hardware | SFX
7 | Connect on-board sensors to the API/software | 5 | 4 |  | Hardware/Software | Other
8 | Mobile version of the web-app for interacting with the polypod | 5 | 1 |  | Software
9 | Live camera feed from the polypod through the web-app | 5 | 5 |  | Software
10 | Record voice lines | 1 | 4 |  | SFX
11 | Emotion detection of the user and corresponding polypod reaction | 8 | 3 |  | Software
12 | Draw mouth animation for opening to critter scene | 3 | 2 |  | Artwork
13 | Object detection through the camera. ("Get off your phone!") | 8 | 4 |  | Software
14 | User analytics based on camera detections (how long you've been at your desk, etc.) | 5 | 4 |  | Software
15 | Environment analytics (average temperature, humidity, etc.) | 5 | 3 |  | Software
16 | Reaction to external stimuli based on web notifs of what the user is interested in | 3 | 1 |  | Software
17 | CAD of roll-up isopod case to house the Pi, sensors, and speaker | 13 | 4 |  | 3D Design
18 | Set visual timer / alarm on device (pomodoro) | 3 | 3 |  | Software
19 | Web application allows users to select what they're interested in | 3 | 1 |  | Software
20 | Web application has simple login system so that a user can edit their preferences | 3 | 1 |  | Software
21 | Find APIs for basic notification types. (Sports, Stocks, Weather) | 3 | 2 |  | Project
22 | Switch to softly shut down device when not in use, located in case. | 3 | 2 |  | Hardware
23 | Reactions to loud sounds | 1 | 4 |  | Hardware/Software
24 | Reactions to high/low temperatures | 1 | 4 |  | Hardware/Software
25 | Reactions to touches/bumps | 1 | 4 |  | Hardware/Software
27 | Hardware startup procedure for polypod device | 3 | 2 |  | Hardware
28 | Create initial polypod setup procedure for app | 3 | 3
29 | Create user database (log in, interests, polypod connection) | 5 | 1 |  | Software
30 | Modular widget system for polypod lower screen persistent data, timers, controls | 5 | 2 |  | Software
31 | Connect create connection point for hardweare to server | 3 | 2 |  | Software
32 | Connect humidity sensor | 1 | 1 |  | Hardware
33 | Connect temperature sensor | 1 | 1 |  | Hardware
34 | Connect microphone | 1 | 1 |  | Hardware
35 | Connect speaker | 1 | 1 |  | Hardware
36 | Connect camera | 1 | 1 |  | Hardware
37 | Connect air pressure sensor | 1 | 1 |  | Hardware
38 | Animation for critter dance | 5 | 2 |  | Artwork
39 | LED eyes for conveying emotion | 3 | 2 |  | Hardware/Software
40 | Screensavers (mouths that open up when activity detected) | 3 | 2 |  | Software
41
42
43
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per instructions leave blank for now