## Sheet1
Requirement ID | Detailed Description | Story Points | Priority | Sprint Number | Labels | Who is doing
1 | Create BOM of hardware parts | 2 | 1 | 1 |  | Riley A and Ryland
3 | Measure hardware dimensions to begin CAD design of the case | 5 | 1 | 1 | 3D design | Ryland
20 | Simple login system that is mobile compatable | 5 | 1 | 1 | software, web app | Colin
21 | Allow users to select what they're interested in | 8 | 1 | 1 | software, web app | Colin
32 | Create user database | 5 | 1 | 1 | software
36 | Create bottom screen GUI | 8 | 1 | 1
37 | Initalize NPM workspace and packages | 1 | 1 | 1
39 | CRUD operations for Users | 3 | 1 | 1
40 | Create polling system to connect to external APIs | 8 | 1 | 1
45 | Create Bottom housing | 3 | 1 | 1 | 3D design | Ryland
4 | Pet-like maintenance system/stats and interactions (happiness/mood, etc.) | 3 | 3 | 2 | software | Riley A and Ryland
5 | Modular data source API system (stocks, sports, ...) (connect polywork to polypod) | 8 | 1 | 2 | software | Hannah and Riley A
9 | Connect speaker | 1 | 1 | 2 | hardware | Ryland
11 | Connect camera | 1 | 1 | 2 | hardware | Ryland
12 | Connect environmental sensor(s) | 3 | 1 | 2 | hardware | Aiden
13 | Hardware startup procedure for polypod device | 3 | 2 | 2 | hardware, software | Riley M
14 | Create prototype board for connecting RGB LED eyes | 3 | 2 | 2 | hardware, software | Riley M
19 | Find APIs for basic notification types | 3 | 2 | 2 | project | Hannah and Riley A
48 | Make the selected preferences box on the main page a button | 2 | 2 | 2 | software | Colin
50 | Create small API/driver for controlling the RGB LED eyes | 3 | 2 | 2 | hardware, software | Riley M
51 | create login and connect server to front end | 5 | 2 | 2 | software | Hannah and Colin
53 | Configure backend to read and parse sensor data | 5 | 2 | 2 | software | Aiden
6 | Connect website to server | 3 | 1 | 3 | software | Hannah and Colin
15 | Polypod reactions to touch/bumps | 1 | 4 | 3 | hardware, software | Aiden
16 | Reactions to high/low temperatures | 1 | 4 | 3 | hardware, software | Aiden
18 | A physical switch to softly shutdown device when not in use | 3 | 2 | 3 | hardware
23 | Live camera feed section | 3 | 2 | 3 | software, web app
24 | Create page for current statistics/recorded data | 3 | 2 | 3 | software, web app
7 | Web application can communicate with polypod via API | 5 | 2 | 4 | software, web app | Colin
22 | Mobile version of the web-app | 3 | 3 | 4 | software, web app
26 | Set a visual timer/alarm on the device | 3 | 3 | 4 | software | Riley A
27 | Polypod reactions to web notifications/api polls | 3 | 1 | 4 | software | Riley A
31 | Create API for hardware to server | 3 | 2 | 4 | hardware, software | Riley M
33 | Implement a live camera feed into the API | 5 | 3 | 4 | software | Riley M
28 | Mouth animation for opening to critter scene | 3 | 2 | 5 | artwork | Riley A
29 | Animation for critter dance | 5 | 2 | 5 | artwork | Riley A
30 | Implement screensavers | 3 | 2 | 5 | software | Riley A
25 | Voice lines | 1 | 4 | 6 | sfx
34 | Object detection through the camera | 8 | 4 | 6 | software | Riley M and Ryland
35 | Emotion detection through camera | 8 | 3 | 6 | software | Riley A