## Sheet1
Requirement ID | Detailed Description | Story Points | Priority | Sprint Number | Labels | Assignees
22 | Mobile version of the web-app | 3 | 3 | 4 | software, web app | ColinTreanor
23 | Live camera feed section | 3 | 2 | 4 | software, web app | ColinTreanor
74 | Move the application onto the server | 8 | 1 | 4 | software, web app | hrsmith1, rileyAnde
7 | Web application can communicate with polypod via API | 5 | 2 | 4 | software, web app | rileyAnde, hrsmith1
31 | Create API for hardware to server | 3 | 2 | 4 | hardware, software | m-riley04
33 | Implement a live camera feed into the API | 5 | 3 | 4 | software | m-riley04
78 | Add new api's that can be toggled | 3 | 2 | 4 | software | Ryland
79 | Improve UI for settings and media | 3 | 2 | 4 | software | Ryland
80 | Add API for live sports scores & notifications | 3 | 2 | 4 | software | aidenhburke
81 | Poll weather API for live weather updates | 3 | 2 | 4 | software | aidenhburke
64 | Make flutter app use IPC for both windows
69 | Add touchups for device loading |  |  |  |  | m-riley04