## Sheet1
Requirement ID | Detailed Description | Story Points | Priority | Sprint Number | Labels | Assignees
1 | Create BOM of hardware parts | 2 | 1 | 1
3 | Measure hardware dimensions to begin CAD design of the case | 5 | 1 | 1 | 3D design | Ryland-Edwards
20 | Simple login system that is mobile compatable | 5 | 1 | 1 | software, web app | ColinTreanor
21 | Allow users to select what they're interested in | 8 | 1 | 1 | software, web app | ColinTreanor
32 | Create user database | 5 | 1 | 1 | software | hrsmith1
36 | Create bottom screen GUI | 8 | 1 | 1 |  | rileyAnde
37 | Initalize NPM workspace and packages | 1 | 1 | 1 |  | hrsmith1
39 | CRUD operations for Users | 3 | 1 | 1 |  | hrsmith1
45 | Create Bottom housing | 3 | 1 | 1 | 3D design | Ryland-Edwards
4 | Pet-like maintenance system/stats and interactions (happiness/mood, etc.) | 3 | 3 | 2 | software | rileyAnde
5 | Modular data source API system (stocks, sports, ...) | 8 | 1 | 2 | software | hrsmith1
13 | Hardware startup procedure for polypod device | 3 | 2 | 2 | hardware, software | m-riley04
14 | Create prototype board for connecting RGB LED eyes | 3 | 2 | 2 | hardware, software | m-riley04
19 | Find APIs for basic notification types | 3 | 2 | 2 | project | Ryland-Edwards, hrsmith1, aidenhburke, rileyAnde
48 | Make the selected preferences box on the main page a button | 2 | 2 | 2 |  | ColinTreanor
50 | Create small API/driver for controlling the RGB LED eyes | 3 | 2 | 2 | hardware, software | m-riley04
53 | Configure backend to read and parse sensor data | 2 | 2 | 2 | software | aidenhburke
54 | Make rpi UI multi-window | 4 | 5 | 2 | software | m-riley04
6 | Connect website to server | 3 | 1 | 3 | software | ColinTreanor
9 | Connect speaker | 1 | 1 | 3 | hardware | Ryland-Edwards
11 | Connect camera and provide setup procedure | 1 | 1 | 3 | hardware | m-riley04
12 | Connect environmental sensor(s) | 3 | 1 | 3 | hardware | aidenhburke
16 | Reactions to high/low temperatures | 1 | 4 | 3 | hardware, software | aidenhburke
18 | A physical switch to softly shutdown device when not in use | 3 | 2 | 3 | hardware | m-riley04
40 | Create polling system to connect to external APIs | 8 | 1 | 3 |  | rileyAnde
63 | Polypod first-time USER setup/settings | 5 | 1 | 3 | hardware, software | m-riley04
69 | Add touchups for device loading | 2 | 1 | 3 | hardware, software | m-riley04
76 | Add CLI to help with debugging polypod app on non-RPI devices | 3 | 3 | 3 | software | m-riley04
68 | User can deselect pereferences from summary button | 2 | 4 | 3 |  | ColinTreanor
7 | Web application can communicate with polypod via API | 5 | 2 | 4 | software, web app | rileyAnde
22 | Mobile version of the web-app | 3 | 3 | 4 | software, web app | ColinTreanor
23 | Live camera feed section | 3 | 2 | 4 | software, web app | ColinTreanor
26 | Set a visual timer/alarm on the device | 3 | 3 | 4 | software | rileyAnde
27 | Polypod reactions to web notifications/api polls | 3 | 1 | 4 | software | rileyAnde
33 | Implement a live camera feed into the API | 5 | 3 | 4 | software | m-riley04
78 | Add new api's that can be toggled | 3 | 2 | 4 | software | Ryland-Edwards
79 | Improve UI for settings and media | 2 | 2 | 4 | software | Ryland-Edwards
80 | Add API for live sports scores & notifications | 2 | 2 | 4 | software | aidenhburke
70 | Remove Email from Database | 2 | 2 | 4 |  | hrsmith1
73 | expose interest list to the frontend | 2 | 2 | 4 |  | hrsmith1
28 | Mouth animation for opening to critter scene | 3 | 2 | 5 | artwork
29 | Animation for critter dance | 5 | 2 | 5 | artwork
30 | Implement screensavers | 3 | 2 | 5 | software
31 | Create API for hardware to server | 3 | 2 | 5 | hardware, software | m-riley04
34 | Object detection through the camera | 8 | 4 | 5 | software | Ryland-Edwards, m-riley04
85 | Have live sports score updates for 'followed' games | 5 | 2 | 5 | software, web app | aidenhburke
86 | connect flutter frontend to weather api | 2 | 2 | 5 | software | Ryland-Edwards
81 | Poll weather API for live weather updates | 2 | 2 | 5 |  | aidenhburke
25 | Voice lines | 1 | 4 | 6 | sfx
35 | Emotion detection through camera | 8 | 3 | 6 | software